## Research and Adoption: Jobspeaker Pilot & CRM Research (regional decision)

| Jun | Jul | Aug | Sept | Oct | Nov | Dec |
| --- | --- | --- | --- | --- | --- | --- |
| - Pilot data collection - Mapping activities - Submit interim pilot report - Research CRMs in use | - Pilot data collection - Mapping activities - Refine CRM requirements | - Pilot data collection - Finalize CRM requirements and rubric | - Pilot data collection - Evaluate leading CRM tools - Submit CRM recommendations | - Pilot data collection - Work with pilot colleges on post-pilot needs | - Submit final pilot report - Develop plans for end of pilot licenses | - Transition activities from pilot licenses to full implementation |

## Research, Evaluation, and Dissemination: Career Exploration & Student Success Tools/Technologies (local decision)

| Jun | Jul | Aug | Sept | Oct | Nov | Dec |
| --- | --- | --- | --- | --- | --- | --- |
| - Research CEX technology options and develop product dossiers | - Finalize CEX product dossiers - Research existing SS tools use - Update SS product dossiers | - WG3 meeting to evaluate CEX products - Develop recommendations for SS tool features and use of tools | - Support colleges as requested in assessing technology options to meet recommendations and college needs | - Support colleges as requested in assessing technology options to meet recommendations and college needs | - Inform year 2 PN plans as they relate to technology adoption |  |