2020-21 DRAFT Workgroup 1 Priority Projects

| Scope of Work | Goal | Priority 2020-21 Project | 2020-21 Activities |
| --- | --- | --- | --- |
| Pathway Awareness and Pathway Organization & Development | #3 | 1. Complete Program Finder Tools - Practitioner program finder tool - Public facing program finder tool for parents, counselors, and students | - Confirm and communicate current status - Bring the public facing program finder tool to the career pathways group to help increase awareness - Finalize and validate content - Demonstrate the final public facing tool - Promote the pubic facing tool to stakeholders (including counselors) |
| Pathway Awareness and Pathway Organization & Development | #3 | 2. Establish sustainable cycle for updates and use of the K-12 to CC Program Finder Tool | - Clarify roles and responsibilities – who owns these tools? (who will update them and how) - Develop timeline and agreement for participation (data sharing and/or general agreement to provide updates on x date, etc., etc.) - Establish metrics for evaluating success of the tools and opportunities for improvement |
| Pathway Awareness and Pathway Organization & Development | #3 | 3. Promote and improve upon the K-12 to CC public facing program finder tool. | - Training awareness campaign - Marketing campaign (present in break-out session at counselors conference) - Evaluation & usage campaign |
| Pathway Organization & Development | #1, 2, 3, 4, 5, 6 (Ties to all goals) | 3. Build an intentional Pathways Partnership CoP to improve communication and awareness across practitioner segments and to provide shared learning opportunities | - Structure Pathways Partnership meetings with standard agenda items – focus on communication, updates, sharing, and group learning opportunities - Showcase promising practices - Provide shared learning experiences on WBL and early college credit (to include virtual opportunities) - Provide round table opportunity for all participants - Include regular updates from: - Regional Directors - COE on Labor Market Demand updates - Marketing committee - MS/HS engagement committee - Adult ed committee - K12 TAP and K12 Pathways Coordinators - Community College outreach roles - CCTE Directors - County Office of Education - K12SWP - Adopt Workforce Pathways Guiding Policy Principles, elements of high quality college and career pathway, and working norms for fostering mutually beneficial intersegmental relationships |
| Quality Pathway Components And Pathway Success | #6 | 5. Map the early college credit landscape and identify activities for expanding and strengthening early college credit opportunities within career education pathways | - Regroup on current project status - Collect existing data elements - Reevaluate and/or complete survey project to identify strengths and areas in need of improvement - Identify strengths and areas in need of improvement. Use process and/or report to inform 2021-22 activities and/or regional investments |
| Pathway Organization & Development and Pathway Success | #4 | 4. Leverage data to increase shared understanding of K12 career education students, career education pathways success, and career education transitions (including adult ed) | - Identify existing reports, share what already exists and work to create a regional timeline - Identify existing reporting that can be collected and combined for a regional view - Identify gaps in existing reporting, shared definitions, etc. - Propose a regional research project |